## 12-Month Roadmap
Phase | Sprint/Month | Epic | Story ID | Story Title | Story Description | Priority | Story Points | Dependencies | Acceptance Criteria
Q1: Foundation
Q1: Foundation | M1 | Architecture & Infrastructure | ARCH-001 | Define system architecture | Document iOS app architecture: MVVM-C pattern, CarPlay integration layer, GPT service, location service, audio engine | P0 | 8 |  | Architecture doc reviewed and approved by engineering leads
Q1: Foundation | M1 | Architecture & Infrastructure | ARCH-002 | Set up CI/CD pipeline | Configure Xcode Cloud or Fastlane for build, test, and TestFlight distribution | P0 | 5 |  | Automated builds trigger on PR merge to main
Q1: Foundation | M1 | Architecture & Infrastructure | ARCH-003 | Set up backend infrastructure | Provision API gateway, GPT proxy service, and session state storage (CloudKit or custom backend) | P0 | 8 |  | API endpoints return 200 in staging environment
Q1: Foundation | M1 | Architecture & Infrastructure | ARCH-004 | Implement GPT proxy service | Build backend proxy that manages OpenAI API keys, rate limiting, and cost controls per account | P0 | 8 | ARCH-003 | Proxy forwards requests to GPT and enforces per-account rate limits
Q1: Foundation | M1 | Architecture & Infrastructure | ARCH-005 | Define data models and API contracts | Specify models for Session, Round, Question, Score, Account; define REST/gRPC contracts | P0 | 5 |  | API contracts documented in OpenAPI spec and reviewed
Q1: Foundation | M1-M2 | Authentication & Accounts | AUTH-001 | Implement Sign in with Apple | Full SIWA flow with persistent token storage in Keychain | P0 | 5 |  | User signs in via Apple ID and session persists across app restarts
Q1: Foundation | M2 | Authentication & Accounts | AUTH-002 | Implement email magic link auth | Passwordless email login with one-time link | P1 | 5 | ARCH-003 | User receives email, taps link, and is authenticated in-app
Q1: Foundation | M2 | Authentication & Accounts | AUTH-003 | Implement email/password auth | Standard email and password registration and login with secure storage | P1 | 5 | ARCH-003 | User registers, logs in, and credentials stored securely
Q1: Foundation | M2 | Authentication & Accounts | AUTH-004 | Implement Google and Facebook auth | OAuth 2.0 flows for Google and Facebook login | P2 | 5 | ARCH-003 | User authenticates via Google or Facebook and session persists
Q1: Foundation | M2 | Authentication & Accounts | AUTH-005 | Implement silent re-authentication | Token refresh without user interaction; handle expiry gracefully | P0 | 3 | AUTH-001 | Expired tokens refresh silently; user never sees re-login prompt
Q1: Foundation | M2 | Authentication & Accounts | AUTH-006 | Implement account deletion | In-app account deletion per App Store guidelines | P0 | 3 | AUTH-001 | User deletes account from iPhone settings; all data removed within 48 hours
Q1: Foundation | M2 | Authentication & Accounts | AUTH-007 | Block login UI in CarPlay | CarPlay never displays authentication screens per CP-AUTH-01 | P0 | 2 | AUTH-001 | No auth UI appears on CarPlay display under any condition
Q1: Foundation | M2-M3 | CarPlay UI & Session Lifecycle | CPUI-001 | Build CarPlay Home screen | Implement CPTabBarTemplate or CPListTemplate with Start New Game and Resume Last Game | P0 | 5 |  | CarPlay displays two options; Resume appears only when resumable state exists
Q1: Foundation | M2-M3 | CarPlay UI & Session Lifecycle | CPUI-002 | Implement CarPlay template navigation | Build template stack for game flow: Home, Playing, Round Summary, Lightning Round | P0 | 8 | CPUI-001 | User navigates through all game states without template errors
Q1: Foundation | M3 | CarPlay UI & Session Lifecycle | CPUI-003 | Build voice wizard for new session setup | Voice-only flow: ask number of people, age bands, confirm difficulty. No required touch | P0 | 8 | VOICE-001 | Driver sets up game entirely by voice; no touch required
Q1: Foundation | M3 | CarPlay UI & Session Lifecycle | CPUI-004 | Implement session state persistence | Save session state after every question and scoring event; efficient writes that do not block UI | P0 | 5 | ARCH-005 | State persists across app kills and CarPlay disconnects
Q1: Foundation | M3 | CarPlay UI & Session Lifecycle | CPUI-005 | Build Resume Last Game flow | Restore session state and speak recap: question number, round, score | P0 | 5 | CPUI-004 | Resume restores exact game position and speaks correct summary
Q1: Foundation | M2-M3 | Voice Engine (STT/TTS) | VOICE-001 | Integrate Apple Speech framework for STT | On-device speech recognition with continuous listening in bounded answer window | P0 | 8 |  | App transcribes spoken answers with 90%+ accuracy in car environment
Q1: Foundation | M3 | Voice Engine (STT/TTS) | VOICE-002 | Integrate AVSpeechSynthesizer for TTS | Text-to-speech for questions, hints, results, and game flow prompts | P0 | 5 |  | All game text spoken clearly at appropriate speed and volume
Q1: Foundation | M3 | Voice Engine (STT/TTS) | VOICE-003 | Implement audio session management | Configure AVAudioSession for CarPlay: handle interruptions, ducking, and focus | P0 | 8 |  | Audio pauses for calls/Siri/nav and resumes correctly
Q1: Foundation | M3 | Voice Engine (STT/TTS) | VOICE-004 | Build always-listening answer capture | Continuous listening with crosstalk detection and final-answer prompting (ANS-01 through ANS-03) | P0 | 8 | VOICE-001 | System detects multiple voices and prompts for final answer; caps at 2 retries
Q2: Core Gameplay
Q2: Core Gameplay | M4 | GPT Integration | GPT-001 | Build question generation prompt | Design GPT prompt that generates 5 questions, answers, hints, rubric per round based on location, difficulty, age bands | P0 | 8 |  | Single GPT call returns structured JSON with 5 complete question payloads
Q2: Core Gameplay | M4 | GPT Integration | GPT-002 | Build answer grading prompt | Design GPT prompt for grading with strictness tiers: lenient (Simple) to near-exact (Einstein) | P0 | 8 | GPT-001 | Grading returns correct/incorrect within latency targets per difficulty tier
Q2: Core Gameplay | M4 | GPT Integration | GPT-003 | Implement challenge re-grade flow | Second-pass GPT call with stricter double-check instruction; one per question, standard rounds only | P1 | 5 | GPT-002 | Challenge triggers re-grade; score updates if overturned
Q2: Core Gameplay | M4 | GPT Integration | GPT-004 | Build GPT response parser | Parse structured JSON responses; handle malformed responses with retry logic | P0 | 5 | GPT-001 | Parser extracts all fields; retries once on malformed response
Q2: Core Gameplay | M4 | GPT Integration | GPT-005 | Implement cost controls | One GPT call per round; cap rerolls at 2; cap challenges; rate limit abusive patterns per account | P0 | 5 | ARCH-004 | No account exceeds defined cost thresholds; soft limits trigger first
Q2: Core Gameplay | M4 | Location Services | LOC-001 | Implement location manager | iOS CLLocationManager with appropriate permissions and accuracy for area-level resolution | P0 | 5 |  | App obtains location permission and provides coordinates
Q2: Core Gameplay | M4 | Location Services | LOC-002 | Build human-readable label generator | Reverse geocode to format: Near {town}, {state} ({major city} area). Never send coordinates to GPT | P0 | 5 | LOC-001 | Label matches LOC-05 format; no coordinates in GPT payloads
Q2: Core Gameplay | M4 | Location Services | LOC-003 | Implement location fallback logic | Fall back to broader region/state when location unavailable or question quality is low | P1 | 3 | LOC-002 | System gracefully degrades from local to regional to state-level trivia
Q2: Core Gameplay | M4-M5 | Standard Gameplay | GAME-001 | Build question loop (Q1-Q5) | Present question via TTS, listen for answer, grade, announce result, advance to next | P0 | 13 | GPT-001, VOICE-004 | Five questions play in sequence with correct scoring
Q2: Core Gameplay | M5 | Standard Gameplay | GAME-002 | Implement multiple choice for Simple mode | Display A/B/C/D options on CarPlay; accept spoken letter or option text | P0 | 5 | GAME-001 | Simple mode shows four choices; voice input accepts letter or full answer
Q2: Core Gameplay | M5 | Standard Gameplay | GAME-003 | Implement free-response for Tricky/Hard/Einstein | Accept open-ended spoken answers with difficulty-appropriate grading strictness | P0 | 5 | GAME-001, GPT-002 | Free-response answers graded per difficulty strictness tier
Q2: Core Gameplay | M5 | Standard Gameplay | GAME-004 | Build hint system | Voice command triggers pre-generated hint; one per question; track usage | P1 | 3 | GPT-001 | Saying 'hint' speaks one hint; second request denied; counter incremented
Q2: Core Gameplay | M5 | Standard Gameplay | GAME-005 | Build round summary screen | Announce round score, cumulative score, hints used, challenges used; display on CarPlay | P0 | 5 | GAME-001 | Summary spoken and displayed after Q5 with accurate stats
Q2: Core Gameplay | M5 | Standard Gameplay | GAME-006 | Build continue/end prompt | Voice Yes/No with large touch button fallback; route to next round or end session | P0 | 3 | GAME-005 | User continues or ends by voice or touch; state saved correctly
Q2: Core Gameplay | M5 | Standard Gameplay | GAME-007 | Implement category selection and reroll | GPT selects category per round; voice command 'pick another category' regenerates; cap at 2 rerolls | P1 | 5 | GPT-001 | Category announced at round start; reroll generates new category and questions
Q2: Core Gameplay | M5 | Standard Gameplay | GAME-008 | Implement grading feedback audio | Play game-show thinking music during grading; duck other audio appropriately | P1 | 3 | VOICE-003 | Thinking sting plays during grading wait; volume ducked correctly
Q2: Core Gameplay | M5 | Standard Gameplay | GAME-009 | Build clarification flow | If GPT grading returns uncertain, ask for clarification once and re-grade (CLAR-01, CLAR-02) | P1 | 5 | GPT-002, VOICE-004 | Uncertain grade triggers one clarification prompt; second attempt graded or skipped
Q2: Core Gameplay | M6 | Lightning Round | LTNG-001 | Offer Lightning Round after 4 standard rounds | Track completed rounds; prompt offer after every 4th round | P0 | 3 | GAME-006 | Lightning Round offered at rounds 4, 8, 12, etc.
Q2: Core Gameplay | M6 | Lightning Round | LTNG-002 | Build 120-second timer | Countdown timer displayed on CarPlay; auto-end at expiry | P0 | 5 | CPUI-002 | Timer counts down and round ends immediately at 0:00
Q2: Core Gameplay | M6 | Lightning Round | LTNG-003 | Implement rapid MCQ flow | Multiple choice for all difficulties; fast question cycling; accept A/B/C/D by voice | P0 | 8 | GAME-002 | Questions cycle rapidly; voice input accepted; score tallied in real time
Q2: Core Gameplay | M6 | Lightning Round | LTNG-004 | Disable hints and challenges in Lightning Round | Block hint and challenge voice commands during Lightning Round | P1 | 2 | LTNG-003 | Hint and challenge commands return denial message during Lightning Round
Q2: Core Gameplay | M6 | Lightning Round | LTNG-005 | Build Lightning Round results summary | Announce questions answered, correct count, and return to standard flow | P0 | 3 | LTNG-003 | Results spoken and displayed; game returns to continue/end prompt
Q3: Polish & Launch
Q3: Polish & Launch | M7 | Interruption Handling & Resume | INT-001 | Implement auto-pause on interruption | Detect incoming call, Siri, nav prompt, audio focus loss, CarPlay disconnect; checkpoint state | P0 | 8 | VOICE-003, CPUI-004 | Game pauses instantly on any interruption; state saved
Q3: Polish & Launch | M7 | Interruption Handling & Resume | INT-002 | Build post-interruption recovery prompt | After interruption ends, ask: resume, restart current round, or end game | P0 | 5 | INT-001 | Three options presented by voice; selection routes correctly
Q3: Polish & Launch | M7 | Interruption Handling & Resume | INT-003 | Handle Lightning Round interruption | Pause countdown timer on interruption; resume or end Lightning Round | P1 | 3 | LTNG-002, INT-001 | Timer pauses and resumes at correct time; option to end offered
Q3: Polish & Launch | M7 | Interruption Handling & Resume | INT-004 | Handle network loss gracefully | Detect connectivity loss; queue pending actions; display clear messaging; retry on reconnect | P0 | 5 |  | User sees clear message; game resumes when network returns
Q3: Polish & Launch | M7 | Interruption Handling & Resume | INT-005 | Handle GPS loss gracefully | Fall back to last known area label or broad region when GPS unavailable | P1 | 3 | LOC-003 | Game continues with last known location; no crash or blank state
Q3: Polish & Launch | M7-M8 | Analytics & Monitoring | ANAL-001 | Instrument session analytics | Track sessions started, sessions completed, session duration, rounds per session | P1 | 5 |  | Analytics dashboard shows session metrics within 24 hours
Q3: Polish & Launch | M8 | Analytics & Monitoring | ANAL-002 | Instrument gameplay analytics | Track rounds played, lightning rounds played, hint rate, challenge rate, challenge overturn rate | P1 | 5 | ANAL-001 | Gameplay metrics visible in analytics dashboard
Q3: Polish & Launch | M8 | Analytics & Monitoring | ANAL-003 | Instrument performance metrics | Track grading latency distribution, GPT call success rate, STT accuracy indicators | P0 | 5 | ANAL-001 | P95 latency and error rates visible in monitoring dashboard
Q3: Polish & Launch | M8 | Analytics & Monitoring | ANAL-004 | Implement crash-free session tracking | Integrate crash reporting; track crash-free session rate as key metric | P0 | 3 |  | Crash-free rate displayed on dashboard; alerts at threshold drops
Q3: Polish & Launch | M8-M9 | Testing & QA | TEST-001 | Build unit test suite for core game logic | Cover scoring, round flow, state management, difficulty rules | P0 | 8 |  | 80%+ code coverage on game logic modules
Q3: Polish & Launch | M9 | Testing & QA | TEST-002 | Build integration tests for GPT service | Test generation, grading, challenge flows with mock and live GPT | P0 | 5 | GPT-001 | All GPT integration paths tested with expected response validation
Q3: Polish & Launch | M9 | Testing & QA | TEST-003 | Build CarPlay UI tests | Test template navigation, voice wizard, interruption handling on CarPlay simulator | P0 | 5 | CPUI-002 | All CarPlay flows pass on simulator
Q3: Polish & Launch | M9 | Testing & QA | TEST-004 | Conduct in-vehicle road testing | Test in real vehicles across 3+ CarPlay head units; validate voice performance in car noise | P0 | 8 |  | Game completes full sessions in 3+ vehicle types without critical issues
Q3: Polish & Launch | M9 | Testing & QA | TEST-005 | Load and stress testing on backend | Validate GPT proxy, session storage, and auth under peak concurrent users | P1 | 5 | ARCH-003 | Backend handles 10x expected peak with <5s P95 latency
Q3: Polish & Launch | M9 | App Store & CarPlay Compliance | COMP-001 | CarPlay entitlement and review prep | Apply for CarPlay entitlement; ensure compliance with all CarPlay HIG requirements | P0 | 5 |  | CarPlay entitlement approved by Apple
Q3: Polish & Launch | M9 | App Store & CarPlay Compliance | COMP-002 | Privacy and data handling compliance | Implement App Tracking Transparency; no persistent age storage; no audio to GPT; no coordinates to GPT | P0 | 5 |  | Privacy manifest complete; all data handling per PRD privacy rules
Q3: Polish & Launch | M9 | App Store & CarPlay Compliance | COMP-003 | App Store submission and review | Prepare screenshots, metadata, review notes; submit for review | P0 | 3 | COMP-001, COMP-002 | App approved and live on App Store
Q3: Polish & Launch | M9 | App Store & CarPlay Compliance | COMP-004 | Implement age-appropriate content safeguards | Ensure GPT prompts enforce kid-safe content; validate output filtering | P0 | 3 | GPT-001 | No inappropriate content generated across 1000 test rounds
Q4: Growth & Future
Q4: Growth & Future | M10 | Post-Launch Optimization | OPT-001 | Optimize grading latency | Profile and reduce GPT grading round-trip; target P95 under 3 seconds | P1 | 5 | ANAL-003 | P95 grading latency drops below 3 seconds
Q4: Growth & Future | M10 | Post-Launch Optimization | OPT-002 | Optimize STT accuracy in noisy environments | Test alternative speech recognition configurations; implement noise cancellation if available | P1 | 5 | VOICE-001 | STT accuracy improves by 10%+ in road noise conditions
Q4: Growth & Future | M10 | Post-Launch Optimization | OPT-003 | Implement question quality feedback loop | Track skip rates and challenge rates by question; flag low-quality patterns for prompt tuning | P1 | 5 | ANAL-002 | Low-quality questions identified and prompt adjusted within 2 weeks of detection
Q4: Growth & Future | M10-M11 | Multi-Car Gameplay (Roadmap) | MULTI-001 | Design multi-car architecture | Document real-time sync protocol for 2-4 cars playing together; evaluate WebSocket vs peer-to-peer | P2 | 8 |  | Architecture doc reviewed; technology choice made and validated
Q4: Growth & Future | M11 | Multi-Car Gameplay (Roadmap) | MULTI-002 | Build lobby and car pairing system | Create/join game lobby via share code; sync session state across cars | P2 | 13 | MULTI-001 | Two cars pair via code and see shared game state
Q4: Growth & Future | M11-M12 | Multi-Car Gameplay (Roadmap) | MULTI-003 | Implement per-car scoring and leaderboard | Track scores per car; display comparative standings after each round | P2 | 8 | MULTI-002 | Each car sees own score and relative position after every round
Q4: Growth & Future | M12 | Multi-Car Gameplay (Roadmap) | MULTI-004 | Build multi-car end-of-game summary | Final standings, winning car announcement, total questions answered per car | P2 | 5 | MULTI-003 | End screen shows ranked results for all participating cars
Q4: Growth & Future | M11-M12 | Monetization Foundation (Roadmap) | MON-001 | Design premium tier feature set | Define what goes behind paywall: additional difficulty modes, longer sessions, ad-free, multi-car | P2 | 3 |  | Feature matrix approved by product and business stakeholders
Q4: Growth & Future | M12 | Monetization Foundation (Roadmap) | MON-002 | Implement StoreKit 2 subscription framework | Build subscription purchase, restore, and entitlement checking | P2 | 8 | MON-001 | Test subscriptions work in sandbox environment
Q4: Growth & Future | M12 | Monetization Foundation (Roadmap) | MON-003 | Build paywall UI on iPhone | Subscription offer screen accessible from iPhone settings; never shown in CarPlay | P2 | 5 | MON-002 | Paywall displays on iPhone; no paywall UI on CarPlay
Q4: Growth & Future | M12 | Social Features (Roadmap) | SOC-001 | Design social sharing and leaderboards | Spec sharing results to iMessage/social; global and friends leaderboards | P2 | 3 |  | Social feature spec reviewed and prioritized for next roadmap cycle

## Epic Summary
Epic Name | Total Stories | Total Story Points | Phase | Key Dependencies | Description
Architecture & Infrastructure | 5 | 34 | Q1 (M1) | None | System architecture, CI/CD, backend, GPT proxy, data models
Authentication & Accounts | 7 | 28 | Q1 (M1-M2) | ARCH-003 | All auth providers, silent re-auth, account deletion, CarPlay auth blocking
CarPlay UI & Session Lifecycle | 5 | 31 | Q1 (M2-M3) | VOICE-001 | Home screen, template navigation, voice wizard, state persistence, resume
Voice Engine (STT/TTS) | 4 | 29 | Q1 (M2-M3) | None | On-device STT, TTS, audio session management, always-listening capture
GPT Integration | 5 | 31 | Q2 (M4) | ARCH-004 | Question generation, grading, challenge, response parsing, cost controls
Location Services | 3 | 13 | Q2 (M4) | None | Location manager, human-readable labels, fallback logic
Standard Gameplay | 9 | 50 | Q2 (M4-M5) | GPT-001, VOICE-004 | Question loop, MCQ, free-response, hints, scoring, categories, grading audio
Lightning Round | 5 | 21 | Q2 (M6) | GAME-002 | Timer, rapid MCQ, hint/challenge blocking, results summary
Interruption Handling & Resume | 5 | 24 | Q3 (M7) | VOICE-003, CPUI-004 | Auto-pause, recovery prompt, Lightning pause, network/GPS loss
Analytics & Monitoring | 4 | 18 | Q3 (M7-M8) | None | Session, gameplay, performance metrics, crash tracking
Testing & QA | 5 | 31 | Q3 (M8-M9) | All core epics | Unit tests, integration tests, CarPlay tests, road testing, load testing
App Store & CarPlay Compliance | 4 | 16 | Q3 (M9) | COMP-001 | Entitlement, privacy compliance, submission, content safeguards
Post-Launch Optimization | 3 | 15 | Q4 (M10) | ANAL-003 | Latency, STT accuracy, question quality feedback loop
Multi-Car Gameplay (Roadmap) | 4 | 34 | Q4 (M10-M12) | None | Architecture, lobby, per-car scoring, end-of-game summary
Monetization Foundation (Roadmap) | 3 | 16 | Q4 (M11-M12) | None | Premium tier design, StoreKit 2, paywall UI
Social Features (Roadmap) | 1 | 3 | Q4 (M12) | None | Sharing and leaderboard design spec

## Timeline View
Epic | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
Architecture & Infrastructure | bar: M1 to M2
Authentication & Accounts | bar: M1 to M2
CarPlay UI & Session Lifecycle | bar: M2 to M3
Voice Engine (STT/TTS) | bar: M2 to M3
GPT Integration | bar: M4
Location Services | bar: M4
Standard Gameplay | bar: M4 to M5
Lightning Round | bar: M6
Interruption Handling & Resume | bar: M7
Analytics & Monitoring | bar: M7 to M8
Testing & QA | bar: M8 to M9
App Store & CarPlay Compliance | bar: M9
Post-Launch Optimization | bar: M10
Multi-Car Gameplay (Roadmap) | bar: M10 to M12
Monetization Foundation (Roadmap) | bar: M11 to M12
Social Features (Roadmap) | bar: M12
| Q1: Foundation |  |  | Q2: Core Gameplay |  |  | Q3: Polish & Launch |  |  | Q4: Growth & Future